## Description and Releases
Scope
The game simulates a social network where the player's main goal consists in expanding it's own network, both in terms of number of acquaitances and in terms of the strenght of the stablished relationships. The player advances through the game by fullfilling a series of in-game missions that, upon completion, will allow to increase it's social network
Group
Class | 3DG
Enterprise | NaaITek
Number | Name of group members
1100859 | André Silva
1110119 | Artur Teixeira
1111168 | João Carreira
1110333 | Tiago Pacheco
Sprint Planning
Code | Begin | End | N. of Days | Status | Observations
1 | 2013-12-11 | 2013-12-16 | 5 | Completed
2 | 2013-12-17 | 2013-12-26 | 7 | Completed | No work at 24/12 and 25/12
3 | 2013-12-27 | 2014-01-05 | 8 | Completed | No work at 31/12 and 01/01
4 | 2014-01-06 | 2014-01-13 | 7 | Completed | Final delivery is in 15/01
Foreseen
Ongoing
Completed

## Prod Backlog
ISSUE | Description | Status | Developer(s)
1 | Create Bootstrap for 3D tests | Completed | AS,AT
2 | Design graph node | Completed | AS,AT
3 | Design graph path | Completed | AS,AT
4 | Create knowledge basis bootstrap | Completed | JC,TP
5 | Implement depth search algorithm | Completed | JC,TP
6 | Implement branch and bound search algorithm | Completed | JC,TP
7 | Dynamic manipulation of knowledge basis (basic AI) | Completed | JC,TP
8 | Implement wide search algorithm | Completed | JC,TP
9 | Setup basic Prolog webservice | Completed | JC, TP
10 | Setup basic JSON parser in C++ | Completed | AS, AT
11 | Improve graph search algorithms | Completed | AS
12 | Improve Prolog webservice | Completed | AS
13 | Implement AI ("CRUD" on knowledge base) | Completed | AS
14 | Enable authentication and roles | Completed | AT
15 | Create bootstrap for website | Completed | AT
16 | Enable globalization (language-wise) | Completed | AT
17 | Minigame: tic-tac-toe | Completed | TP
18 | Minigame: labyrinth | Completed | TP
19 | Minigame: hangman | Completed | TP
20 | Create login to 3D | Completed | JC
21 | Improve graph design | Completed | JC
22 | Create TAGs | Completed | AT
23 | Service returning user's graph | Completed | AS
24 | Connect C++ to Database | Completed | AS
25 | Tic-Tac-Toe Logic | Completed | AT
26 | Hangman Logic | Completed | AT
27 | Labyrinth Logic | Completed | AS
28 | Suggest Connection | Completed | AT
29 | Add and remove friends | Invalid
30 | Network dimension (all users) | Completed | AS
31 | Network dimensions (for authenticated user) | Completed | AS
32 | Leaderboards | Completed | AS
33 | Tag Cloud (All users) | Completed | AS
34 | Tag Cloud (users) | Completed | AS
35 | Friend Suggestion | Completed | AS
36 | Edit connections between users | Completed | AS
37 | User authentication window (visual c++) | Completed | JC
38 | Add friend | Completed | AS
39 | Remove friend | Completed | AS
40 | Check HTTP access | Completed | AS
41 | Check all active webservices | Completed | AS
42 | Check free disk space | Completed | AS
43 | Check CPU usage | Completed | AS
44 | Check network interface usage | Completed | AS
45 | Check number of registered users | Completed | TP
46 | Check download tax | Unresolved | JC
47 | Nodes and paths visual improvement | Completed | AS
48 | Overall graphical improvements | Completed | AT
49 | Associate mini-games | Completed | AS
50 | Connect c++ to prolog ws | Completed | AS
51 | Game Modes | Unresolved
52 | Add sound to the game | Completed | AT
53 | Show the common friends with another friend in another graph | Completed | AS
54 | Create a graph with common friends between two users | Completed | AS
55 | Send friend requests in-game | Completed | AT
56 | Show the shortest and the strongest path between two users | Completed | AS
57 | friend Suggestion | Completed | JC
58 | List the network strenght for each user | Completed | AS
59 | Read notifications | Completed | AT
60 | Add words for Hangman minigame on the website | Completed | TP
61 | Show user names | Completed | AT
62 | Implement external menus | Completed | AT
63 | Viewport for user notification | Completed | JC